Form EOI-1

# EOI Submission Form

[Location, date]

[Authorized official]

Re: Consulting Services for [insert assignment]

Ref: [insert]

We, the undersigned, declare that:

- We are expressing our interest in providing the consulting services for the above-mentioned assignment and have no reservations to the REOI, the instructions to the consultants and any addenda thereto.

- Our expression of interest is open for acceptance for a period of ninety (90) days.

- Our firm, its associates, including any subcontractors or suppliers for any part of the contract, have not been declared ineligible by the Fund and have not been subject to sanctions or debarments under the laws or official regulations of the client’s country or not been subject to a debarment recognized under the Agreement for Mutual Enforcement of Debarment Decisions (the "Cross-Debarment Agreement"), beyond those declared in paragraph 9 of this EOI submission form.

- We acknowledge and accept the IFAD Revised Policy on Preventing Fraud and Corruption in its Activities and Operations. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any prohibited practices as provided in ITC Clause 6. Further, we acknowledge and understand our obligation to report to anticorruption@ifad.org any allegation of prohibited practice that comes to our attention during the selection process or the contract execution.

- No attempt has been made or will be made by us to induce any other consultant to submit or not to submit an EOI for the purpose of restricting competition.

- We acknowledge and accept the IFAD Policy on Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any sexual harassment, sexual exploitation or abuse. Further, we acknowledge and understand our obligation to report to ethicsoffice@ifad.org any allegation of sexual harassment, sexual exploitation and abuse that comes to our attention during the selection process or the contract execution.

- The following commissions, gratuities, or fees have been paid or are to be paid with respect to the selection process: [Insert complete name of each recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity.]

| Name of Recipient | Address | Reason | Amount | Currency |
| --- | --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- We declare that neither our consulting firm nor any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners have any actual, potential or perceived conflict of interest as defined in ITC Clause 5 regarding this selection process or the execution of the contract. [insert if needed: “other than the following:” and provide a detailed account of the actual, potential or perceived conflict]. We understand that we have an ongoing disclosure obligation on such actual, potential or perceived conflicts of interest and shall promptly inform the client and the Fund, should any such actual, potential or perceived conflicts of interest arise at any stage of the procurement process or contract execution.

- The following criminal convictions, administrative sanctions (including debarments) and/or temporary suspensions have been imposed on our consulting firm and/or any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners:

| Nature of the measure (i.e., criminal conviction, administrative sanction or temporary suspension) | Imposed by | Name of party convicted, sanctioned or suspended (and relationship to the consultant) | Grounds for the measure (i.e., fraud in procurement or corruption in contract execution) | Date and time (duration) of measure |
| --- | --- | --- | --- | --- |

If no criminal convictions, administrative sanctions or temporary suspensions have been imposed, indicate “none”.

- We acknowledge and understand that we shall promptly inform the client about any material change regarding the information provided in this EOI submission form.

- We further understand that the failure to properly disclose any of information in connection with this EOI submission form may lead to appropriate actions, including our disqualification as consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

- We understand that you are not bound to accept any EOI that you may receive.

| [Authorized signatory] |  |
| --- | --- |
| [Name and title of signatory] |  |
| [Name and address of firm] |  |

## Form EOI-2 
Organization of the Consultant

Re: Consulting Services for [insert assignment]

Ref: [insert]

[Provide a brief description of the background and organization of your firm/entity and of each associated firm for this assignment. Include the organization chart of your firm/entity. The EOI must demonstrate that the consultant has the organizational capability and to carry out the assignment. The qualifications document shall further demonstrate that the consultant has the capacity to field and provide experienced replacement personnel on short notice. Key staff CVs are not required at the shortlisting stage.]

| Name of the firm |  |
| --- | --- |
| Date of establishment |  |
| Country of registration |  |
| Full address of the firm |  |
| Focal point: name, position, contact information (telephone, email): | Name: |
|  | Tel: |
|  | Email: |
| Number of branches in the country |  |
| Country(ies) of operations with number of branches in each country |  |
| Number of full-time employees |  |
| Number of part-time employees |  |
| Field(s)of expertise of the firm |  |
| Number of professional staff with experience related directly to the assignment |  |
| Subsidiary and associated companies (wherever applicable): (details in the following format to be provided for all associates) – - Name of the company - Nature of business - Address of the company - Website of the company - Brief description of company (maximum of 120 words) |  |
| Any other information that the consultant would like to add: |  |

Maximum 10 pages

## Form EOI-3

## Experience of the Consultant

Re: Consulting Services for [insert assignment]

Ref: [insert]

[Using the format below, provide information on each relevant assignment for which your firm, and each associate for this assignment, was legally contracted either individually as a corporate entity or as one of the major companies within an association, for carrying out consulting services similar to the ones requested under the preliminary terms of reference included in this EOI. The EOI must demonstrate that the consultant has a proven track record of successful experience in executing projects similar in substance, complexity, value, duration, and volume of services sought in this procurement.

Maximum 20 pages]

| Assignment name: | Approx. value of the contract (in current US$): |
| --- | --- |
| Country: Location within country: | Duration of assignment (months): |
| Name of client: | Total No. of staff-months of the assignment: |
| Address, and contact details (including email address(es)): | Approx. value of the services provided by your firm under the contract (in current US$): |
| Start date (month/year): Completion date (month/year): | No. of professional staff-months provided by associated consultants: |
| Name of associated consultants, if any: | Name of proposed senior professional staff of your firm involved and functions performed (indicate most significant profiles such as project director/coordinator, team leader): |
| Narrative description of project: |  |
| Description of actual services provided by your staff within the assignment: |  |

Name of Firm: _________________________________

ANNEX 1

PRELIMINARY TERMS OF REFERENCE

TERMS OF REFERENCE (ToR) FOR POLICY AND REGULATORY REFORM TO IMPROVE SMALLHOLDER FARMERS’, WOMEN’S AND YOUTH’S ACCESS TO LAND, FINANCE, AND QUALITY TECHNICAL AND MATERIAL INPUTS

- BACKGROUND

The Federal Government of Nigeria has received a Facility from the African Development Bank (AfDB), International Fund for Agricultural Development (IFAD) and the Islamic Development Bank (IsDB) to finance the cost of the Special Agro-Industrial Processing Zones Program (SAPZ), and intends to apply part of the proceeds towards carrying out various consultancy services. The SAPZ Program is being implemented in the seven (7) States and the Federal Capital Territory (FCT). The States are Cross River, Imo, Kaduna, Kano, Kwara, Ogun and Oyo.

The overall development objective of the SAPZ programme is twofold: (1) Support the development of SAPZ in high food production areas to supply the domestic food market and create exportable surpluses; and (2) Capacitate smallholder farmers, small agro-processors and traders, and community-based service providers, including women and youth; to take advantage of the market demand created by the SAPZ to sustainably enhance their income, household food security and resilience to climate change.

The programme has four components namely:

➢Component 1: Infrastructure Development and Management for Agro-Industrial Hubs (AIHs). Under this AfDB-led component, the programme will support the FGN in developing and setting up SAPZs in high potential states.

➢Component 2: Agricultural Productivity, Production, Market Linkages and Value Addition in SAPZ Catchment Areas. Under this component, SAPZ’s objective is threefold: (i) support smallholder farmers and small operators to increase their productivity/production and capacity to add value to raw materials on a profitable and environmentally sustainable basis; and (ii) link them to the additional market outlets offered by the Agro-Industrial Hubs (AIHs), off-takers supplying the local and national market who operate in the target area, and small processors/traders supplying the local markets, including primary processors operating in the Agricultural Transformation Centres (ATCs); iii) enhance the resilience and adaptive capacity of smallholder farmers to climate change..

➢Component 3: Policy and Institutional Development Support. The objective of component 3 is to support the development of enabling policies, legislation, and regulation for SAPZs in Nigeria to create a conducive business environment for private sector investment and to address inefficiencies and market failures in agricultural value chains.

➢Component 4:  Programme Coordination and Management. This component will ensure that the programme is efficiently and effectively managed to achieve expected results.

The Special Agro-Industrial Processing Zones (SAPZ) Programme is a flagship initiative of the Federal Government of Nigeria, supported by development partners, aimed at promoting agro-industrialization, enhancing agricultural productivity, strengthening value chains, and improving livelihoods through inclusive and market-oriented agribusiness development.

The SAPZ Programme, supported by IFAD and other development partners, aims to transform rural economies by establishing agro-industrial corridors that link smallholder farmers to processing and markets. Despite significant investments in infrastructure and value chains, smallholders—especially women and youth—face persistent barriers in accessing land, finance, and quality inputs. Existing policies remain fragmented, outdated, or poorly enforced, limiting agro-industrial growth and inclusive participation.

This ToR governs the engagement of a Policy and Regulatory Reform Consultant/Team to develop three priority policy frameworks that will enable an enabling, investment-friendly, and inclusive environment for smallholder-driven agro-industries.

Rationale for Policy and Regulatory Reform

Despite Nigeria's vast agricultural potential, smallholder farmers particularly women and youth continue to face structural barriers that limit their participation in agro-industrial value chains. These barriers include insecure land tenure arrangements, restricted access to affordable finance, inadequate access to certified quality inputs, and persistent resource conflicts. Additionally, the absence of coherent and enforceable policy frameworks governing land access, farm security, agro-enterprise development, and dispute resolution creates an enabling environment deficit that undermines smallholder productivity and investment confidence.

The SAPZ Programme, through Component 3, recognizes that infrastructure development and productivity support alone are insufficient to transform Nigeria's agro-industrial landscape. Structural and systemic constraints embedded in the policy and regulatory environment must be addressed to create durable, inclusive, and commercially viable agro-industrial ecosystems. This requires targeted policy reform, institutional strengthening, and the development of practical frameworks that explicitly address the needs of marginalized groups particularly smallholder farmers, women, and youth.

Against this backdrop, the National Programme Coordination Office (NCO) invites competent consulting firms or consortia with demonstrated expertise in agricultural policy, legal and regulatory reform, land governance, and rural finance to provide technical support for the development and operationalization of three interrelated policy reform areas under the SAPZ Programme, as detailed in this Terms of Reference.

Policy Reform Areas Covered by this ToR

This ToR covers three specific SAPZ policy reform areas under Component 3, as follows:

| S/N | Policy Reform Area | Focus |
| --- | --- | --- |
| 1 | SAPZ Policy Agenda in Support of Smallholder Agro-Industries | Comprehensive policy framework for smallholder agro-industrial participation, competitiveness, and inclusive value chain integration |
| 2 | SAPZ Policy on Conflict Management and Alternative Dispute Resolution (ADR) | Formal mechanisms for managing and resolving disputes arising from land, resources, contracts, and inter-community tensions within SAPZ operational areas |
| 3 | SAPZ Policy on Access to Farmland, Farm Security and Production Inputs for Smallholder Farmers | Governance frameworks to secure smallholder land rights, ensure farm security, and guarantee equitable access to quality production inputs |

2. OBJECTIVES

2.1 Overall Development Objective

The overall objective of this assignment is to support the SAPZ Programme in developing, consulting on, and facilitating the adoption of a coherent, gender-responsive, and youth-inclusive policy and regulatory reform agenda that removes structural barriers to smallholder farmer access to land, finance, quality inputs, and agro-industrial opportunities, thereby strengthening the enabling environment for inclusive and sustainable agro-industrial transformation in Nigeria's SAPZ states.

2.2 Specific Objectives

The specific objectives of this consultancy are as follows:

- Develop a comprehensive SAPZ Policy Agenda in Support of Smallholder Agro-Industries that promotes smallholder competitiveness, market linkages, financial inclusion, and value chain integration within the SAPZ framework.

- Design a robust SAPZ Policy on Conflict Management and Alternative Dispute Resolution (ADR) that establishes clear, accessible, gender-sensitive, and culturally appropriate mechanisms for preventing, managing, and resolving disputes in SAPZ operational areas.

- Formulate a comprehensive SAPZ Policy on Access to Farmland, Farm Security, and Production Inputs for Smallholder Farmers that addresses land tenure insecurity, farmland access barriers, farm-level security threats, and inequitable access to quality agricultural inputs.

- Conduct multi-stakeholder consultations and participatory policy development processes that ensure the voices of smallholder farmers, women, youth, persons with disabilities, and marginalized groups are meaningfully incorporated into policy design.

- Build the capacity of relevant national and state-level policy institutions, implementing agencies, and community organizations to implement, monitor, and evaluate the developed policy frameworks.

- Develop implementation roadmaps, regulatory guidance notes, and institutional arrangements for the rollout of the three policy reform areas across SAPZ states.

3. SCOPE OF WORK

The Consultant(s)/Firm will undertake a comprehensive set of tasks across three integrated policy reform components. The work shall be executed in close collaboration with the NCO, relevant Federal Ministries, Departments and Agencies (MDAs), state-level Programme Implementation Units (PIUs), and key stakeholders.

3.1 Pillar A — SAPZ Policy Agenda in Support of Smallholder Agro-Industries

- Map the smallholder agro-industrial ecosystem within SAPZ host states.

- Review existing policies including NATIP, National Development Plan, MSME Policy, Cooperative Development Policy, and relevant financing instruments.

- Identify policy gaps constraining smallholder linkage to SAPZ anchor firms.

- Propose policy measures to strengthen contract farming, support women- and youth-led MSMEs, streamline licensing, mainstream climate-smart approaches, and establish a SAPZ Smallholder Inclusion Compact.

3.2 Pillar B — SAPZ Policy on Conflict Management and Alternative Dispute Resolution

- Conduct conflict mapping and political-economy analysis across SAPZ host and catchment states.

- Review existing legal frameworks including the Constitution, Land Use Act, Arbitration and Mediation Act, and related instruments.

- Design a SAPZ ADR architecture with grievance redress mechanisms and escalation pathways.

- Define institutional roles for PMUs, ministries, traditional councils, and civil society.

- Recommend capacity-building and accreditation frameworks for SAPZ mediators and ADR practitioners.

3.3 Pillar C — SAPZ Policy on Access to Farmland, Farm Security, and Production Inputs

- Diagnose land governance bottlenecks under the Land Use Act and customary tenure systems.

- Assess gender- and youth-specific barriers to land access.

- Propose reforms for land banks, titling systems, farm security, input supply systems, mechanization, irrigation, and climate-resilient inputs.

- Recommend measures to de-risk smallholder finance through guarantees and blended finance mechanisms.

4.0 QUALIFICATIONS/COMPETENCIES

The Firm should meet the following requirements:

- The assignment is open to consulting firms, academic institutions, research organizations, NGOs, or consortia with demonstrable expertise in agricultural policy, land governance, legal and regulatory reform, and rural development.

- Consortia must identify a lead organization that shall be legally responsible for contract performance. Sub-consultants or consortium partners must be clearly identified in the proposal.

- The firm/consortium must demonstrate a minimum of ten (10) years of relevant experience in policy reform, legal and regulatory advisory services, and/or rural development programming in Sub-Saharan Africa, preferably in Nigeria or West Africa.

- Demonstrated experience of conducting at least three (3) similar assignments involving agricultural policy reform, land governance, ADR system design, or agricultural input supply chain reform in developing country contexts in the last ten years.

- Knowledge and experience of the region and Nigeria in particular is an advantage.

(a) Lead Consultant/Agricultural Policy Expert: Should have a PhD or Master's degree in Agricultural Economics, Agricultural Policy, Development Economics, or related field with experience in agribusiness and value chain development.

- Must have at least 15 years experience in agricultural policy reform, agro-industrial development, or rural development programming; demonstrated experience leading multi-country policy assignments

- Deep understanding of agro-industrial zones or value chain development programs in emerging markets.

- Must have completed at least three (2) of similar assignments in the last ten (10) years

- Demonstrated expertise in land tenure, dispute resolution, agro-industry support, or input systems (at least two of the three).

- Must have experience in participatory stakeholder engagement in Nigeria.

- Must have experience in training, organizational development, and business development.

- Legal and Regulatory Reform Specialist:  should have Academic qualifications of at least a Master's degree or LLB/LLM in Law, specializing in agricultural law, property law, or commercial law or related fields.

- Must have at least 10 years experience in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage

- Must have completed at least two (2) of similar assignments in the last ten (10) years

- Must have experience in participatory stakeholder engagement in Nigeria.

- Knowledge and experience of the region and Nigeria in particular is an advantage

- Gender, Youth and Social Inclusion Specialist:  Must have a Master's degree in Gender Studies, Social Sciences, Development Studies, or related field.

- Should have 8 years experience in conducting gender and social inclusion analyses and mainstreaming gender in agricultural or rural development programmes; experience with women's land rights and youth employment

- Demonstrated experience in gender inclusion activities in the agricultural sector three (3) of which are donor funded projects.

- Must have experience working with the private sector and in developing gender-inclusive financial products and services targeting women entrepreneurs.

- Conflict Management and ADR Specialist : Should have a Master's degree in Peace and Conflict Studies, Law (ADR/Arbitration), Mediation, or related field; certified mediator or arbitrator preferred.

- Should have 10 years experience in designing or implementing conflict management or ADR systems in rural or agricultural contexts in developing countries; experience with farmer-herder conflicts an advantage

- Must have completed at least two (2) of similar assignments in the last ten (10) years

- Must have experience in participatory stakeholder engagement in Nigeria.

- Knowledge and experience of the region and Nigeria in particular is an advantage

- Agricultural Extension /Agricultural Input Supply Chain Specialist:  should have Academic qualifications of at least a Master’s degree in Agricultural Extension, Agronomy, Supply Chain Management or related fields with experience in Agribusiness and Value Chain Development.

- Must have 10 years experience in agricultural input supply chain development, agro-dealer network strengthening, fertilizer or seed systems reform, or agro-input quality assurance

- Must have completed at least two (2) of similar assignments in the last ten (10) years

- Knowledge and experience of the region and Nigeria in particular an advantage.

5.0  DELIVERABLES

The successful Consultants/Firm shall deliver the following milestones to SAPZ as time-lined below:

| MILESTONES |  |  | TIMEFRAME |
| --- | --- | --- | --- |
| S/NO | TASK | DELIVERABLE |  |
| 1 | Inception Report | Inception report detailing the methodology and tools to be used for assignment. | Two weeks after signing of contract agreement. |
| 2 | Mid Term Report | The Draft Diagnostic and Policy Gap Analysis Report (three pillars): Draft Policy A — SAPZ Policy Agenda in Support of Smallholder Agro-Industries, Draft Policy B — SAPZ Policy on Conflict Management and ADR, Draft Policy C — SAPZ Policy on Access to Farmland, Farm Security and Production Inputs as well as the Stakeholder Validation Workshop Reports. | 10th week of signing contract agreement |
| 3 | Final Report | Final three Policy Documents with Roadmaps and Action Plans incorporating observations raised on the draft reports. | 12th week of signing agreement |
| 4 | TOTAL CONSULTANCY TIME |  | 12 weeks |

Payment Schedule

- 20% of the contract sum upon submission of APG and inception report acceptable by SAPZ.

- 50% of the contract sum upon submission and acceptance of draft final report

- 30% of the contract sum upon submission of the final report acceptable to SAPZ and IFAD.

6.0 OUTCOMES/OUTPUTS

At the end of the assignment, the following outputs/outcomes are expected:

- Policy Documents with Roadmaps and Action Plans developed.

- Comprehensive SAPZ Policy Agenda for Inclusive Smallholder Agro-industrial Development;

- SAPZ Policy on Conflict Management and Alternative Dispute Resolution (ADR);

- SAPZ Policy on Access to Farmland, Farm Security and Production Inputs for Smallholder Farmers;

- Improved access to land, finance, quality inputs and extension services for smallholder farmers, women and youth;

- Strengthened institutional coordination, conflict resolution and farm security systems;

- Increased participation of women, youth, farmer organizations and private sector actors in agro-industrial value chains;

- Operational implementation frameworks, action plans and policy reform reports for effective SAPZ implementation.

7.0 	INSTITUTIONAL ARRANGEMENTS

Responsibilities of the Client (SAPZ)

SAPZ shall be responsible for the following:

- The Rural Institutions Development Officer (RIDO) at the National Coordination Office, Abuja shall be the Focal Person for the assignment.

- SAPZ shall allow the consultant access to past reports/documents that may be relevant to the assignment

Responsibilities of the Consultant

I. The Consultant shall be responsible for his/her accommodation and transportation expenses while carrying out the assignment.

ii.     Bears cost of logistics (transport) for official movements for  its team  relating  to this task.

iii.	Bear the cost of production of reports and related documents.

iv. The Lead Consultant shall be the Focal Person of the assignment for the Firm.

8.0 PROCUREMENT METHOD

The Procurement method for the Least Cost Selection (LCS) Method.

9.0	 PROPOSED DURATION OF ASSIGNMENT

It is envisaged that the consultancy will take 12 weeks from the time the contract is signed. The Consultant/Consultancy Firm should develop a feasible cost-work plan/activity schedule covering a maximum of 100 days and submit as integral part of the proposal for this consultancy.

10.0	 REPORT SUBMISSION

A total of Six (6) copies of the reports are to be submitted to the National Programme Coordinator at the National Coordination Office, Abuja.

## Proposal Evaluation Framework

| Item | ANNEX 2: Criteria | Points |
| --- | --- | --- |
| A. | Firm's/Academic/Research Institutions/NGOs general experiences/expertise and qualification | 10 |
| I | Firm’s/Academic/Research Institutions/NGOs with demonstrable expertise in agricultural policy, land governance, legal and regulatory reform, and rural development in the last 10 years or above with evidence of business registration certificate | 10 |
| II | Firm’s/Academic/Research Institutions/NGOs with demonstrable expertise in agricultural policy, land governance, legal and regulatory reform, and rural development in the last 8-9 years or above with evidence of business registration certificate. | 8 |
| III | Firm’s/Academic/Research Institutions/NGOs with demonstrable expertise in agricultural policy, land governance, legal and regulatory reform, and rural development in the last 6 -7 years with evidence of business registration certificate | 6 |
| IV | Firm’s/Academic/Research Institutions/NGOs with demonstrable expertise in agricultural policy, land governance, legal and regulatory reform, and rural development in the last 4 -5 years with evidence of business registration certificate | 4 |
| B. | Specific experience | 30 |
| I | Experience in the successful execution of at least 5 projects of a similar nature and scope of works under MDBs funded project in the last 10 years | 30 |
| II | Experience in the successful execution of 4 projects of a similar nature and scope of works under MDBs funded project in the last 10 years | 25 |
| III | Experience in the successful execution of 3 projects of a similar nature and scope of works under MDBs funded project in the last 10 years | 20 |
| C | Firm’s Financial / Account Information with Evidence of Tax Clearance (TCC) and Audited Accounts for 2023, 2024 & 2025 | 10 |
| I | Firm’s financial/account information with 3 years of the relevant audited accounts and TCC | 10 |
| II | Firm’s financial/account information with 2 years of the relevant audited accounts and TCC | 6 |
| III | Firm’s financial/account information with 1 year of the relevant audited accounts and TCC * | 4 |
| IV | Firm’s financial/account information with only audited account | 2 |
| D | The qualifications of the key staff proposed for the Assignment | 50 |
| D1A | Lead Consultant/Agricultural Policy Expert | 10 |
| D1A | At least a Master’s Degree in Agricultural Economics, Agricultural Policy, Development Economics, or related field with at least 10 years’ experience in agribusiness and value chain development | 10 |
| D1A.i | At least a Master’s Degree in Agricultural Economics, Agricultural Policy, Development Economics, or related field with 8-9 years’ experience in agribusiness and value chain development | 8 |
| D1A.ii | At least a Master’s Degree in Agricultural Economics, Agricultural Policy, Development Economics, or related field with 6-7 years’ experience in agribusiness and value chain development | 6 |
|  | At least a Master’s Degree in Agricultural Economics, Agricultural Policy, Development Economics, or related field with 4-5 years’ experience in agribusiness and value chain development | 4 |
| D1B | Specific Competencies and Experience | 10 |
| D1B.i | A proven track record in expertise in land tenure, dispute resolution, agro-industry support, or input systems with at least 3 similar jobs undertaken with MDB in the last 10 years | 10 |
| D1B.ii | A proven track record in expertise in land tenure, dispute resolution, agro-industry support, or input systems with 2 similar jobs undertaken with MDB in the last 10 years | 8 |
| D1B.iii | A proven track record in expertise in land tenure, dispute resolution, agro-industry support, or input systems with 1 similar job undertaken with MDB in the last 10 years | 6 |
| D2A | Legal and Regulatory Reform Specialist/ Conflict Management and ADR Specialist | 10 |
| D2A.i | Master's degree or LLB/LLM in Law, specializing in agricultural law, property law, or commercial law or related fields with at least 10 years of experience in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage | 10 |
| D2A.ii | Master's degree or LLB/LLM in Law, specializing in agricultural law, property law, or commercial law or related fields with 8-9 10 years of experience in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage | 8 |
| D2A.iii | Master's degree or LLB/LLM in Law, specializing in agricultural law, property law, or commercial law or related fields with 6-7 years of experience in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage | 6 |
| D2B | Specific Competencies and Experience | 5 |
| D1B.i | A proven track record in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage with at least 3 similar jobs undertaken with MDB in the last 10 years | 5 |
| D1B.ii | A proven track record in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage with 2 similar jobs undertaken with MDB in the last 10 years | 4 |
| D1B.iii | A proven track record in agricultural legal reform, regulatory advisory, legislative drafting, or policy advocacy; experience with Nigerian legislative processes is an advantage with 1 similar job undertaken with MDB in the last 10 years | 3 |
| D3A | Gender, Youth and Social Inclusion Specialist | 10 |
| D3A.i | Master's degree in Gender Studies, Social Sciences, Development Studies, or related field with at least 8 years of experience in conducting gender and social inclusion analysis and mainstreaming gender in agricultural or rural development programs | 10 |
| D3A.ii | Master's degree in Gender Studies, Social Sciences, Development Studies, or related field with at least 6-7 years of experience in conducting gender and social inclusion analysis and mainstreaming gender in agricultural or rural development programs | 8 |
| D3A.iii | Master's degree in Gender Studies, Social Sciences, Development Studies, or related field with at least 4-5 years of experience in conducting gender and social inclusion analysis and mainstreaming gender in agricultural or rural development programs | 6 |
| D3B | Specific Competencies and Experience | 5 |
| D3B.i | A proven track record in gender inclusion activities in the agricultural sector with at least 3 similar jobs undertaken with MDB in the last 5 years | 5 |
| D3B.ii | A proven track record in gender inclusion activities in the agricultural sector with at least 2 similar jobs undertaken with MDB in the last 5 years | 4 |
| D4B.iii | A proven track record in gender inclusion activities in the agricultural sector with 1 similar job undertaken with MDB in the last 5 years | 3 |
|  | Total | 100 |
|  | Minimum points required to pass | 70 Points |

The Cross-Debarment Agreement was entered into by the World Bank Group, the Inter-American Development Bank, the African Development Bank, the Asian Development Bank and the European Bank for Reconstruction and Development, additional information may be located at: http://crossdebarment.org/.

For guidance on the evaluation of consulting services, please see the corresponding module of the IFAD procurement handbook available at www.ifad.org/project-procurement.